## Sheet1
Sprint |  | Ideal | Actual
9 hours per person per week. (Total 36 hours).
Week 3 | 0 | 306 | 306
Week 4 - Sprint 1 | 18 | 270 | 276
Week 5 - Sprint 2 | 54 | 234 | 246
Week 6 - Sprint 3 | 90 | 198 | 222
Week 7 - Sprint 4 | 126 | 162 | 201 |  | Total class time per week: 18 hours. The 9 extra hours were in case a person was sick and /or to catch up if needed.
Week 8 - Sprint 5 | 162 | 126 | 165
Week 9 - Sprint 6 | 198 | 90 | 117
Week 10 - Sprint 7 | 234 | 54 | 96
Week 11 - Sprint 8 | 270 | 18 | 66
Week 12 - Sprint 9 | 306 | 0 | 66
Hours Spent up to day
Task | Hours | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Customer-Search | 45 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | 53.33% |  |  | Allocated time frame
2. Company-Add | 27 | 4: 9; 5: 9; 6: 9 | 100%
3. User-Reg/Login | 27 | 4: 9; 5: 9; 6: 3; 7: 6 | 100%
4. Admin-Main | 18 | 4: 9; 5: 9 | 100%
5. Customer-Save | 45 |  |  |  | 9 | 9 | 9 | 9 | 9 | 9 |  | 100% | +20%
6. Company-Edit-Res | 18 | 8: 9; 9: 9 | 100%
7. User-Edit-Account | 18 | 7: 3; 8: 15 | 100%
8. Admin-Approve | 27 | 9: 9; 10: 9; 11: 9 | 100%
9. Company-Delete | 9 | 9: 9 | 100%
10. Admin-Delete | 9 | 9: 9 | 100%
11. Admin-Add | 18 | 10: 0; 11: 0 | 0% |  | Note: Customer-Search not completed with allocated time. Admin-Add not completed.
12. Customer-Comment | 18 | 9: 0; 10: 0 | 0% |  | Note: Customer-Comment and Company-Comment were completed with Customer-Save (Surendra)
13. Company-Comment | 18 | 10: 0; 11: 0 | 0%
14. Unallocated (Extra time) | 9 | 11: 9 | 100%
Remaining |  | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 40 | 40
Actual | 306 | 306 | 276 | 246 | 222 | 201 | 165 | 117 | 96 | 66 | 66
Ideal | 306 | 306 | 270 | 234 | 198 | 162 | 126 | 90 | 54 | 18 | 0